| Project Initiation Document (PID) |  |
| --- | --- |
| Project Title | IT Security and Infrastructure Enhancement |
| Company | 57th Global Tyres |
| Prepared by | Owolabi Olasubomi |

Table of Contents

Project Background	3

Mission Statement	3

Vision Statement	3

Project Objectives	3

Departments and Scope of Work	4

Key Deliverables	4

Roles and responsibilities	5

Project Timeline	5

Project Budget	5

Risk Assessment	6

Communication Plan	6

Training & Awareness	6

Monitoring & Review	6

# Project Background

This project simulates the role of an IT professional at 57th Tyres Global, a fast-growing tyre sales and distribution company based in Lagos, Nigeria, that aims for global expansion. The company employs between 50 and 200 people, including on-site and remote staff.

In Lagos’ competitive market, where customer trust is vital, 57th Tyres Global has a strict zero-tolerance policy for actions that could harm its reputation. Protecting customer data, ensuring business continuity, and maintaining operational excellence are core values of the organization.

# Mission Statement

Our goal is to provide durable, safe, and affordable tyres while establishing a standard for excellence and innovation in the automotive industry across Africa and beyond.

# Vision Statement

We aim to be the most trusted tyre brand in West Africa, recognized globally for our quality, customer service, and operational integrity.

# Project Objectives

- Achieve ISO 27001:2022 certification by the end of the project timeline

- Protect sensitive information, including client data, proprietary training materials, and internal intellectual property

- Ensure compliance with relevant regulations, such as GDPR and NDPR

- Enhance the company’s market positions by leveraging ISO 27001:2022 certification

- Establish information security governance and increase the awareness of 57th global tyres team of information security principles

# Departments and Scope of Work

| Department | No. of Users | Critical Assets |
| --- | --- | --- |
| Legal | 5 | Laptops, Legal Document Repository, External Drive, Contract Management Software |
| Human Resources | 6 | HRMIS, Laptops, Payroll Software, Staff Database |
| IT | 8 | Servers, Network Switches, Firewalls, Admin Laptops, Monitoring Tools |
| Supply Chain | 9 | Inventory Software, Laptops, Barcode Scanners, Delivery Schedule System |
| Sales | 10 | CRM, POS Machines, Mobile Devices, Sales Dashboard |
| Facilities | 4 | CCTV Systems, Access Control Units, Maintenance Scheduling Software |
| Operations | 7 | Production System, Industrial PCs, Asset Trackers, Operations Dashboard |

# Key Deliverables

- Asset Inventory by Department

- Security Gap Assessment Report

- Risk Treatment Plan

- Staff Awareness Training

- Policy Documents (Acceptable Use, Access Control, Data Classification)

- Implementation of Antivirus, Firewalls, Backup Systems

- Final Project Report and Recommendations

# Roles and responsibilities

- Project sponsor, [pascal riwaan] CEO – Provides strategic direction and ensure alignment with business goals

- Project manager: [Owolabi Olasubomi] IT contractor – oversee the project, manage resources and ensure timely delivery

- Deaprtment heads – Ensure department specific compliance with ISMS policies

- Employees – participate in trainings and adhere to isms policies

# Project Timeline

| Phase | Duration |
| --- | --- |
| Project Kickoff | 1 Week |
| Asset Inventory & Audit | 2 Weeks |
| Risk & Gap Assessment | 2 Weeks |
| Implementation | 4 Weeks |
| Training & Awareness | 2 Weeks |
| Monitoring Setup | 1 Week |
| Final Review & Reporting | 1 Week |

# Project Budget

# Risk Assessment

| Risk Description | Likelihood | Impact | Mitigation Strategy |
| --- | --- | --- | --- |
| Resistance to change by staff | Medium | High | Conduct awareness sessions and demos |
| Data loss during implementation | Low | High | Perform backups before changes |
| Vendor delays in tool procurement | Medium | Medium | Use multiple vendors; pre-negotiate timelines |
| Incompatibility with legacy systems | Low | Medium | Test updates in sandbox before deployment |
| Budget overrun | Medium | Medium | Track spent weekly and report variances |

# Communication Plan

| Audience | Frequency | Channel | Responsible |
| --- | --- | --- | --- |
| Project Team | Weekly | Email, WhatsApp | Project Lead |
| Management | Bi-weekly | Summary Reports | IT Lead |
| Department Heads | At Milestones | Progress Meetings | Project Lead |
| All Staff | Monthly | Bulletin, Email | HR/Comms |

# Training & Awareness

- Mandatory Cybersecurity Awareness Training for all departments

- Role-specific sessions for HR, Legal, and Sales systems

- Posters, infographics, and email campaigns for reminders

- Post-training assessments to measure understanding

- Optional video tutorials for common IT practices (MFA, backups)

# Monitoring & Review

- Weekly audit logs and monthly reports

- Quarterly internal IT reviews to assess progress

- A post-project review and user feedback survey to identify gaps